AGENDA/STATUS

April 12, 2005, Coordination Committee Meeting

37 Days s to Go!

2005 Westchester Aviation Career Fair, Thursday, May 19th- Friday, May 20th

- Schools- Steve Gross

  - Responses received –1310

    - Distribution between days/ and middle/H.S.

  - Follow-up mailings/phone

    - Finalize school packet to those attending-

    - Last year’s useable with changes

  - Posters for school display-Margaret Walsh

- Exhibitors/activities- Hank

  - Responses received- 35 confirmed, 17 verbal, fax not received

    - Exhibitors-

    - Static display aircraft/equipment- on-going( Layout-Bill Weaver)

  - Finalize exhibit packet to people attending

    - Last year’s useable with changes

    - Send booth invoice w/ packet

  - Exhibitor Parking- Steve Ferguson

  - Exhibitor check-in

  - Special Events (Scenario for scheduling student groups through event presentations)

    - Ribbon Cutting

    - Astronaut attendance – not confirmed

      - Leroy Chiao-returning 4/24th from space station

      - Sally Ride- Dr. Ride retired from NASA in 1987 to become a Science Fellow at the Center for International Security and Arms Control at Stanford University. After two years, she was named Director of the California Space Institute and Professor of Physics at the University of California, San Diego where she pursued one of her heartfelt crusades, encouraging young women to study science and math

    - Jamil Larkin coming both days ( 4/19 , 12:30pm, 4/20  9:00 am –2:00 pm, Joan Brown (FAA), confirmed

    - PAMA Regional Maintenance Olympics-(all sessions)Tim Gronberg ( confirmed)

    - Wright Aeronautical Factory (all sessions)

    - Original Igor Sikorsky 2-axis Helicopter Simulator-also booth

    - P & W Jet Engine Cut-away (may also have booth)

    - Hangar theatre- schedules for videos/DVD’s.

- Facilities- Bob Brunner

  - Skyport Hangar

    - Booth layout- max capacity finalized

    - Electrical requirements (finalized)

    - Audio visual setup- (finalized)

    - Inside static display/ Special Events- in work

  - Outside static display-Bill Weaver, Brian Ciambra( in work)

  - Traffic flow-Bob, Bill, Steve Ferguson –(finalized)

    - Bus Routing

    - Student

  - Additional Security-Brian Ciambra

  - Porta John- Lucy Kropat/Bill Weaver- finalized

  - Trash collection( Steve Ferguson)

- Thursday, May 19th Late afternoon early eve event/program TBD

  - PAMA Olympics to continue

  - Wright Aircraft Factory Presentation

  - Speakers-TBD

  - 4:00 pm –7:00 pm- Buffet dinner

    - Airport/Business Community

    - Sponsors

    - Exhibitors

  - Scouting  Community

  - AOPA –Phil Boyer

- Food- Tony Beadle, Bob, Hank

  - Skytop Restaurant participation

    - Sale to students/exhibitors/ volunteers –to 2b finalized this week (cash and carry)

    - Food for Thursday May 19th late afternoon/early eve /reception event-TBD

- Student Handouts

  - T-shirts- John Johnston

    - Below logo as before, ‘The Sky’s the limit”, no date

    - Above logo, “Launching the Next Century of Flight”

    - Cost Estimate- Lori Rosa

  - Handouts from NASA, Debbie Galloway contacted

  - Jeppesen Catalogues/bags-contacted

  - Gliem, Be a Pilot-finalized

  - FAA bags- Joan Brown

  - Sporty’s cockpit  poster-finalized

  - Discuss- Sponsor/Exhibitor booklet

  - Misc. Handouts

    - Schedule of special event presentations/activities

    - Student Interview Sheets

    - Student evaluation forms

    - Teacher packets (NASA, Debbie Gallaway)

    - Teacher evaluation forms

    - List of Exhibitors

    - Exhibitor Booth Layout

    - A/C & other Equipment Layout

    - Blurbs about exhibitors, A/C, and Equipment

    - List of Sponsors

- Volunteers- John Johnston to finalize requirements

  - (Preliminary) Setup Day, May 18th, 1200 – 1800>>>>

    - PAMA setup

    - Wright Aero Factory setup

    - Exhibitor assistance

    - Ramp/static display control-Bill Weaver

    - Ramp Barricade/fencing-Steve Ferguson, Bob, Bill

  - (Preliminary) Event Days

    - Bus routing

    - Pre-event a/c arrival (before 0800)

    - Ramp/static display control-Bill Weaver

    - Student/Teacher bag distribution, (outside tent(s)

- Develop budget- Hank Grudberg- (All vendor quotes received)

- Treasurer’s Report- Tony Beadle

- Fund Raising Report- Jeff Lee

- Promotion/Advertising/signage

  - Airport- Main sign in house- 2ft x 24ft underhang in the works to be erected corner of Skyport hangar D-3

  - Schools

  - Letter by County Executive to airport/business community-mid-end April.- 2b finalized

  - Other invitations, political, and business leaders for Thursday eve 2b finalized

  - Contact Channel 12, NBC Channel 4, Journal News-Preliminary contact made

- Website (www.aviationeducationcorp.org)- 322 hits

- Other (?)

- Future Meeting Schedules:

  - Tuesday, May 3rd, IBM 10:00 am-11:30 am

  - Tuesday, May 10th, IBM 10:00 am-11:00 am

  - Monday, May 16th, IBM 10:00 am-11:00 am

    - Volunteers needed to assemble student/ teacher bags

  - Tuesday, May 17th, IBM 10:00 am-11:00 am

  - SETUP, Wednesday, May 18th, Skyport Hgr D, 8:00 am